SHAMBA WATCH PROJECT SPECIFICATION

Bill of Materials (BOM) & Labor Estimate

Turnkey Deployment of 6-Station Environmental & Agricultural Telemetry Network across the Rift Valley Basin, Kenya
Naivasha · Ol Kalou · Nakuru Basin · Molo · Elementaita · Gilgil | Exchange Rate: 1 USD ≈ 130 KES

💡 USER INSTRUCTION FOR HYPERLINKS IN MICROSOFT WORD:
• To open any link below in Microsoft Word: Hold the Ctrl key and click (Ctrl + Click).
• Alternatively, right-click any link and choose 'Open Hyperlink', or copy the displayed web address directly into your browser.

――――――――――――――――――――――――――――――――――――――――――――――――――――――――――――――――――――

# 1. Executive Summary & Deployment Architecture

Shamba Watch monitors hydrological, soil chemical, and microclimatic dynamics across 6 sentinel stations in the Kenyan Rift Valley basin. Each station operates autonomously off-grid, transmitting real-time telemetry over cellular LTE-M / NB-IoT to a cloud dashboard.

• Target Field Locations: Naivasha North Plot (Greenhouse), Ol Kalou (Maize), Nakuru Basin (Wetland), Molo (Tea), Elementaita (Rangeland), Gilgil (River Intake).
• Core Sensing Payload: Volumetric soil moisture (10–25cm), Soil NPK (25–40cm), water level transducer, ambient temperature/humidity, and thermal infrared sensor.
• Autonomous Power & Enclosure: 50W Monocrystalline solar PV, 12V 17.5Ah Lithium battery pack, MPPT solar controller, and IP67 NEMA enclosure on a 3.5m anti-tamper mast.
• Sourcing Hubs: Nerokas Online Store (Nairobi) and authorized local distributors (Chloride Exide, Coast Cables, Lafarge/Bamburi Cement, Kirinyaga Road electrical suppliers).

# 2. Hardware Bill of Materials (Priced in KES with Nairobi Links)

## A. Sensor Suite (6 Stations)

| Item | Component | Specification | Unit (KES) | Qty | Total (KES) | Total (USD) | Kenyan Store Source & Web Link |
| --- | --- | --- | --- | --- | --- | --- | --- |
| A1 | Soil Moisture Probe | Multi-depth FDR probe (0–40cm), RS-485 Modbus RTU | 15,000 | 6 | 90,000 | $692.31 | Nerokas: 7-in-1 Sensor https://store.nerokas.co.ke/SKU-3931 |
| A2 | Soil NPK Sensor | Industrial optical/electrochemical probe (N, P, K), RS-485 Modbus | 15,000 | 6 | 90,000 | $692.31 | Nerokas: 7-in-1 NPK https://store.nerokas.co.ke/SKU-3931 |
| A3 | Water Level Transducer | A02YYUW Waterproof Ultrasonic Sensor (IP67, UART/RS485) | 4,000 | 6 | 24,000 | $184.62 | Nerokas: A02YYUW IP67 https://store.nerokas.co.ke/Sensors |
| A4 | Ambient Temp & RH | Sensirion SHT31 Outdoor Temp/Humidity probe with sintered metal mesh | 3,600 | 6 | 21,600 | $166.15 | Nerokas: SHT31 Outdoor https://store.nerokas.co.ke/SKU-3760 |
| A5 | Thermal IR Module | AMG8833 8x8 IR Thermal Camera Breakout (Alt: MLX90614 @ KES 2,100) | 5,000 | 6 | 30,000 | $230.77 | Nerokas: AMG8833 Thermal https://store.nerokas.co.ke/SKU-3295 |
| Subtotal | Sensor Suite Subtotal | Unified 7-in-1 option saves KES 90,000 if A1 & A2 are combined | - | - | KES 255,600 | $1,966.15 | Nerokas Online Store |

## B. Edge Node, Solar Power & Enclosures (6 Stations)

| Item | Component | Specification | Unit (KES) | Qty | Total (KES) | Total (USD) | Kenyan Store Source & Web Link |
| --- | --- | --- | --- | --- | --- | --- | --- |
| B1 | Cellular IoT Gateway | LILYGO T-SIM7600 ESP32 LTE 4G Dev Board (Cat4, GPS, RS-485) | 14,000 | 6 | 84,000 | $646.15 | Nerokas: Cellular IoT https://store.nerokas.co.ke/ |
| B2 | Solar Power System | 50W Monocrystalline PV Panel + adjustable heavy-duty mast bracket | 4,500 | 6 | 27,000 | $207.69 | Chloride Exide Kenya https://chlorideexide.com/ |
| B3 | Battery Storage | TERRAVOLT 12V 17.5Ah Lithium-ion Battery with integrated BMS | 15,000 | 6 | 90,000 | $692.31 | Nerokas: Batteries https://store.nerokas.co.ke/drones-robotics/Batteries |
| B4 | Solar Charge Controller | 10A/20A MPPT Intelligent Solar Regulator (Solar Power Manager) | 2,000 | 6 | 12,000 | $92.31 | Nerokas: Solar Manager https://store.nerokas.co.ke/drones-robotics/Batteries |
| B5 | Weatherproof Enclosure | IP67 Hinged NEMA Polycarbonate Box with mounting plate (280x190mm) | 3,500 | 6 | 21,000 | $161.54 | Nerokas: Enclosures https://store.nerokas.co.ke/index.php?route=product/category&path=65 |
| B6 | Wiring, Glands & Jacks | M12/M16 IP68 Cable Glands, 4-core shielded cable, aviation connectors | 2,500 | 6 | 15,000 | $115.38 | Coast Cables Nairobi https://www.coastcables.com/ |
| Subtotal | Power & Gateway Subtotal | Complete autonomous power & telemetry package | - | - | KES 249,000 | $1,915.38 | Nerokas / Chloride Exide |

## C. Civil Works, Mounting Masts & Physical Security (6 Stations)

| Item | Component | Specification | Unit (KES) | Qty | Total (KES) | Total (USD) | Kenyan Store Source & Web Link |
| --- | --- | --- | --- | --- | --- | --- | --- |
| C1 | Telescopic Sensor Mast | 3.5m Galvanized steel pole (Class B), baseplate, guy wires & turnbuckles | 9,500 | 6 | 57,000 | $438.46 | Nairobi Metal Fabricators |
| C2 | Grounding & Surge Protection | 5ft Copper-bonded earth rod, clamp, 10m 16mm² wire, DC SPD arrester | 5,500 | 6 | 33,000 | $253.85 | Coast Cables Nairobi https://www.coastcables.com/ |
| C3 | Security Perimeter / Cage | Steel anti-vandal lockbox for enclosure + 2mx2m razor wire / chain-link cage | 14,000 | 6 | 84,000 | $646.15 | Local Metal Fabricators |
| C4 | Civil Consumables | 2 bags Bamburi/Simba cement, ballast, quarry sand, 20mm PVC conduit | 4,500 | 6 | 27,000 | $207.69 | Bamburi Cement (Lafarge) https://www.lafarge.co.ke/ |
| Subtotal | Civil & Security Subtotal | Anti-theft, wildlife mitigation & lightning grounding | - | - | KES 201,000 | $1,546.15 | Nairobi Industrial Suppliers |

# 3. Professional Labor & Engineering Services (Standardized at KES 1,700/hr)

| Workstream | Roles & Responsibilities | Hours | Rate (KES/hr) | Total (KES) | Total (USD) |
| --- | --- | --- | --- | --- | --- |
| Firmware & IoT Integration | Hardware engineer: bench-testing, Modbus RS-485 calibration, low-power sleep modes, MQTT schemas | 48 hrs (6d) | 1,700 | 81,600 | $627.69 |
| Backend & Cloud Pipeline | Cloud architect: Firebase/GCP IoT pipeline, Firestore security rules, alert webhooks | 40 hrs (5d) | 1,700 | 68,000 | $523.08 |
| Frontend UI/GIS Integration | Frontend engineer: live Firebase connection, SVG sparklines, Leaflet layer calibration | 32 hrs (4d) | 1,700 | 54,400 | $418.46 |
| Field Agronomy & Soil Baseline | Lead Agronomist: soil core extraction, lab calibration, depth placement verification | 32 hrs (4d) | 1,700 | 54,400 | $418.46 |
| Mechanical & Electrical Rigging | Field crew (2 technicians x 6 days): mast erection, concrete footing, trenching, wiring | 96 hrs (12d) | 1,700 | 163,200 | $1,255.38 |
| Commissioning & Quality Assurance | QA engineer: end-to-end signal tests, satellite/IR feed alignment, network failover | 24 hrs (3d) | 1,700 | 40,800 | $313.85 |
| Farmer & Operator Handover | Extension officer: on-site training for farm managers & coops (Naivasha, Molo, Ol Kalou) | 16 hrs (2d) | 1,700 | 27,200 | $209.23 |
| Subtotal | Professional Engineering & Field Services (288 Hours Total) | 288 hrs | - | KES 489,600 | $3,766.15 |

# 4. Field Logistics & Circuit Travel

| Item | Description / Details | Unit Cost | Qty | Total (KES) | Total (USD) |
| --- | --- | --- | --- | --- | --- |
| Vehicle Hire & Fuel | 4WD vehicle across Nairobi – Naivasha – Nakuru – Molo – Ol Kalou circuit | $120/day | 7 days | 109,200 | $840.00 |
| Field Per Diem & Stays | 3-person deployment team field allowances in Rift Valley | $150/day | 6 days | 117,000 | $900.00 |
| Permits & Wayleaves | County permissions & Water Resources Authority (WARMA) coordination | Lump sum | 1 | 45,500 | $350.00 |
| Subtotal | Logistics, Field Travel & Regional Permits | - | - | KES 271,700 | $2,090.00 |

# 5. Annual Operational Expenditure (Year 1 OpEx)

| Item | Service Details | Monthly (KES) | Annual (KES) | Annual (USD) | Provider & Web Link |
| --- | --- | --- | --- | --- | --- |
| Cellular IoT Data (eSIM) | 6x Safaricom / Airtel IoT M2M SIMs (500MB data pool + SMS alerts) | 3,900 | 46,800 | $360.00 | Safaricom Kenya https://www.safaricom.co.ke/ |
| Cloud Hosting & Database | Firestore reads/writes, Firebase Hosting, Cloud Functions, Alert Webhooks | 3,250 | 39,000 | $300.00 | Google Firebase https://firebase.google.com/ |
| Quarterly Maintenance | Solar panel cleaning, sensor probe descaling, battery load test (4 visits/yr) | 8,667 | 104,000 | $800.00 | Local Field Crew |
| Spare Parts Buffer | Sacrificial sensor cables, replacement fuses, 10% probe contingency | 5,417 | 65,000 | $500.00 | Nerokas / Local |
| Total OpEx | Annual Operating Costs for 6-Station Telemetry Network | KES 21,234/mo | KES 254,800 | $1,960.00 | Year 1 Total |

# 6. Comprehensive Financial Summary (CapEx vs. OpEx)

| Category | Scope Description | Total (KES) | Total (USD) | % of CapEx |
| --- | --- | --- | --- | --- |
| 1. Sensor Hardware | 6 stations x 5 sensor categories (NPK, Moisture, Level, Temp/RH, IR) | 255,600 | $1,966.15 | 16.4% |
| 2. Power & Edge Gateways | 6 stations x Solar panels, MPPT controllers, Li-ion batteries, LTE-M boards | 249,000 | $1,915.38 | 15.9% |
| 3. Civil Works & Security | 6 stations x 3.5m masts, earth grounding, anti-theft cages, concrete footings | 201,000 | $1,546.15 | 12.9% |
| 4. Engineering & Field Labor | 288 billable hours across firmware, cloud, UI, agronomy, installation @ KES 1,700/hr | 489,600 | $3,766.15 | 31.3% |
| 5. Logistics & Travel | 7-day 4WD vehicle hire, technician per diems across Rift Valley, WARMA permits | 271,700 | $2,090.00 | 17.4% |
| Contingency Buffer (8%) | Unforeseen site modifications, spare cables, hardware replacement reserve | 95,616 | $735.51 | 6.1% |
| TOTAL PROJECT CAPEX | Turnkey Procurement, Engineering, Deployment & Handover | KES 1,561,916 | $12,014.74 | 100.0% |
| ANNUAL OPEX (YEAR 1) | Cellular IoT SIMs, Cloud Hosting, Quarterly Field Maintenance & Spares | KES 254,800 | $1,960.00/yr | - |

# 7. Cost Optimization & Implementation Strategy

1. Unified 7-in-1 Probe Optimization: By purchasing the 7-in-1 Soil Sensor from Nerokas (KES 15,000) that integrates Moisture, N, P, K, Temp, EC, and pH into one probe, separate spending for items A1 and A2 is avoided. This directly saves KES 90,000 ($692.31), lowering overall CapEx to KES 1,464,716 ($11,267.05).

2. Phased Deployment Circuit: Deploy two anchor stations first — ST-01 (Naivasha Greenhouse) and ST-06 (Gilgil River Intake) — to validate hydrological and soil telemetry over the local Safaricom IoT cellular network before erecting masts at the remaining 4 remote plots.

3. Anti-Theft & Lightning Mitigation: Given the open rangeland conditions in Elementaita and Molo highlands, the anti-vandal lockable cage and 16mm² copper grounding rod are mandatory safeguards to prevent equipment theft and thunderstorm surge damage.